## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
GUI for a drop down menu |  |  | Done | 6 | 2 | 1 | 0 | 1 | 2 | 0 | 2
Design (UML) |  |  | in progress
GoogleMap API (opening a google map with a location pinpoint) |  |  | Done | 8 | 1 | 2 | 2 | 0 | 3 | 0 | 2
Task
User Story #2 | 1
Task
Task
Task
Task
User Story #3 | 5
Task
Task
Task
Task
User Story #4 | 8
Task
Task
Task
Task
User Story #5 | 3
Task
Task
Task
Task
TOTAL |  |  |  | 14 | 3 | 3 | 2 | 1 | 5 | 0 | 4

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0